## Rational Unified Process Fundamentals, v. 2000.02.10

## Project Simulation

### The Assignment

The assignment is to develop a new computer-based system for a video store company called Movie Corner. The Movie Corner consists of a number of shops, where the customer can rent movies. Today they have 24 shops, 2 warehouses and 123 movie kiosks, distributed in five cities. (A movie kiosk is an automated store, where you can hire video tapes/movies by using a member card).

The development contract has a fixed price and a fixed delivery date. One criterion is also that during the development, Rational Unified Process shall be used.

The business case is to make use of existing techniques, and automate as much as possible (like using the Internet, video kiosks, etc). In addition, they want to have a broad selection of classics, movies for children, etc. The warehouse contains classics as far back as the "Casablanca".

Today, 20,000 titles are available and each shop is hiring out about 1000 movies per day. They carry about 10 copies of the most popular movies. Special movies must be ordered from the warehouse.

### How to Win

The goal is to deliver a computer system with as much functionality as possible and with good quality, but within budget. When the budget (780 000 USD), or the maximum calendar time (43weeks) is exceeded, the team score is reduced.  The team with the best quality and functionality wins.

You should try to complete both Elaboration and Construction before you exceed your cost budget or run past the delivery date.  There is no limit to the number of iterations you can conduct during these phases.

### The Playing Team

### Your team of three to four people will run this project simulation. You will compete with other teams that have exactly the same assignment. All teams will use the iterative approach described in the Rational Unified Process. You may refer to the on-line process as necessary in conducting your project.

Scoring

### Question cards

Correct answers add quality to your project. Your instructor will set the maximum number of questions you may answer per iteration. You do not have to answer any questions in a given iteration. The answer to each question is on the back of the card. You will be responsible for scoring your own answers. Use the on-line process to investigate answers or check your answers before calculating your score. There is a different set of question cards for each phase. If you do not answer all Elaboration questions by LCA, you must return the unanswered questions to the instructor (and therefore lose the opportunity to earn the quality points they represent).

### Event cards

Something unforeseen always happens. You will either profit or lose something. You will take an event card near the end of each iteration, just before the iteration assessment.

Customer tokens

Each team will receive a number of tokens from the instructor. When the team needs to confer with their customer, they must spend a token. Then a team runs out of tokens, they cannot speak to the customer except at the regularly scheduled reviews/meetings. Note, tokens are not meant to be used to ask the instructor for clarification of the rules of the simulation. Such questions can be asked at any time.

Staffing

You may staff your project with up to 10 people. Each person can have from 1 to 3 skills. Available skills are project management, architecture, requirements, design/development, or test. Just like in the real world, the more skills a person has, the more he/she costs. A person with one skill costs $3000 per week. For each additional skill, add $500 per week. Thus, a person will cost either $3000, $3500, or $4000 per week.

Use Case cards

They are predefined and include a short description. They are building the functionality of the system. Not all use cases are known at the start of the project. Implementing use cases allows you to remove project risks. While you may feel that the use cases need modification, or that some use cases are missing, that is not the goal of this exercise. Accept the use cases as they are given, and use them to plan your project.

Simplifications in the Simulation

- The use cases are small and predefined. You are not expected to fix them or add to them.

- The use cases are always fully implemented during an iteration.  (On a real project, use cases may be only partially implemented during an iteration.)

- The risks in the project are predefined and are assigned to use cases. You are not expected to generate more risks or to change assignments.

- We are only using five types of skills: Test, Architecture, Requirement Handling, Design/Development and Project Management. You can combine skills in arbitrary ways.

- A person is either fully engaged, or not at all, during an iteration.

- No one can have more than three skills. By assigning multiple skills, you are asking that individual to work in several different roles within that iteration. If you assign one person three skills, it means that each of the activities they engage in are getting just one-third of a person of effort.

How the Project Works

The Inception Phase is complete. You have an initial set of use cases and a risk list. You are ready to begin the first iteration of the Elaboration Phase. The activities are described in the following diagram:

- Startup

Begin by taking the time to read through all the materials provided by the instructor. Review all the use cases and the risk matrix mapping risks to use cases. The risks have already been prioritized for you.

2. Fill out an Iteration Plan

For each iteration, begin by completing an iteration plan that documents your staffing decisions and the use cases you will address in this iteration. Look at the risk matrix to see which risks you want to address first.  Select the use cases you want to address in this iteration. Decide what skills you need and calculate your burn rate and planned cost and schedule for the iteration.

3. Earn some quality points

Since we cannot expect you to actually implement any software in this simulation, you will instead earn quality points by answering questions about the correct way to conduct the iteration. Your instructor will tell you the maximum number of Question Cards you may answer in one iteration. You do not have to answer any questions in a given iteration. You may answer any number up to the maximum established. Use the on-line process and discuss your answers as a group. When you have an answer, check it with the official answer on the back of the card. Record the number of quality points you’ve earned on your Iteration Assessment form.

4. Take an event card

Go to your instructor and obtain an event card. The event cards introduce some element of uncertainty (and realism) into the simulation. Not every iteration will go as planned. Each card is self-explanatory. Adjust your iteration results based on the instructions on the event card and record them on the Iteration Assessment form.

5. Conduct the iteration assessment

Review the exit criteria for the current phase and determine whether you are ready to move to the next phase. Also, invite your customer (usually the instructor) to review the results of the iteration. Your customer may have new requirements, or may wish to change their mind about something. Your staffing plan will also be reviewed and quality may be adjusted based on skills your staff may be missing. Record the results of the iteration assessment on the form. Make sure to note any lessons learned from the iteration.

6. Decide whether you are done

If you are moving into the Construction Phase, you must change the pile of questions to the ones for the new phase. If you are over budget or over-schedule, your simulation is over. If not, you may move to the next iteration.

7. Conduct the postmortem

When you have finished all iterations, or run out of time or money, calculate your final score. If you have run out of time or money, cut the number of quality points you have earned by half. Multiple the result by the percentage of achieved functionality to calculate your final score. The percentage of achieved functionality is measured as the percentage of total use cases you successfully implemented. The team with the highest score wins!

Work as a team to list the top three things you learned from this exercise. Also, list the one thing you would do differently if you could do the exercise again. Nominate a team leader to present these to the rest of the teams.