## Slide 1
Rational Unified Process Fundamentals Module 6: Iterative Development

## Slide 2: Objectives: Iterative Development
Understand the dynamic structure of RUP by example
Explain the purpose of an iteration plan
Trace the evolution of artifacts between iterations
Use a development case for iterative development
Notes: Be aware that the Development Case found in RUP 2000.02.10 under Artifacts==>Artifact Examples is a link error. This Development Case does NOT belong to the Course Registration System. The student exercise module contains a valid example.

## Slide 3: Review: Core Workflows and Associated Models
OK
OK
Fail
Realized By
Implemented
By
Verified By
Implementation
Model
Test Model
Design Model
Use-Case
Model
Models
Core Process
Workflows
Test
Implemen-
tation
Analysis &
Design
Requirements
Business Use-
Case Model
Business
Modeling
Business
Object Model
B
B
B
B
Realized
By
Automated
By
Notes: Each ‘discipline’ or core workflow has associated with it one or more 'models', which are, in turn, composed of associated artifacts.

## Slide 4: Artifacts Involve More Than One Workflow
Stakeholder
Requests
Vision
Test
Plan
Business
Case
Software
Architecture
Document
Glossary
Use-Case
Model
Supplementary
Specification
Software
Requirements
Specification
Risk
List
Design
Model
Analysis
Model
Software
Development
Plan
Implementation
Model
Deployment
Plan
Notes: Recall that artifacts can be used in more than one core workflow. Thus there is not a one-to-one correspondence between artifact sets and core workflows.
Artifacts are the tangible products of the project: the things the project produces or uses while working toward the final product, which is itself made up of artifacts (e.g. executables, user documentation, etc.).
In this module we follow iteration plans which show the creation and/or modification of example artifacts.
The Course Registration System found in RUP 2000.02.10 at Artifacts==>Artifact Examples is used for the example of this section.
Make sure they know how to find this example. It is the basis of several exercise questions.

## Slide 5: Artifact: Iteration Plan
Time-sequenced set of activities and tasks
Shows resources
Shows dependencies
Sample Iteration Plan: Construction Phase
Notes: Workflow Details can be used to indicate the activities which will occur in a particular iteration.

## Slide 6: Case Study: Selected Iterations and Workflows
Project Management
Environment
Business Modeling
Implementation
Test
Analysis & Design
Phases
Process Workflows
Deployment
Configuration & Change Mgmt
Requirements
Elaboration
Inception
Construction
Transition
Notes: This is based generally on the RUP 5.5 example iterations.
Orient students via this chart so that they don’t lose the context.
There are two Requirements Management walkthroughs so students see an example of artifact evolution (shows different paths in activity diagram).
For each new iteration, orient students with the process overview chart.
Set the context of each iteration.
The relative amount of work related to the workflows changes between iterations and especially between iterations in different phases.

## Slide 7: Assumptions for This Module
Number of iterations
    Inception : 1
    Elaboration : 1
    Construction : 3
    Transition : 2
We only look at 3 of the 7 iterations.
We do not visit all workflows in the 3 selected iterations.
Within an iteration, we treat the workflows sequentially. In fact, many activities would occur in parallel.
This case study is based on the example Course Registration System
We focus on the artifacts specified in the example Development Case.
Notes: Emphasize that we are only following selected workflows and that within an iteration they occur concurrently--even though we walk through them sequentially.

## Slide 8: Case Study: Inception Iteration
Project Management
Environment
Business Modeling
Implementation
Test
Analysis & Design
Phases
Process Workflows
Deployment
Configuration & Change Mgmt
Requirements
Elaboration
Inception
Construction
Transition
Notes: Point out the rectangle and the different colored areas corresponding to each workflow. Ask the students in which workflows most of the effort will be expended.
The relative amount of work related to the workflows changes between iterations and especially between iterations in different phases.

## Slide 9: Context and Objectives: Inception Iteration
We are beginning the initial development cycle for a new product
This is new development which will interface with legacy systems.
The objectives are to define the project Vision and the Business Case
Most of the effort will be spent in the business modeling, environment, requirements, and project management workflows
Notes: The goal of this initial iteration is a first cut at the vision and the business case of the project, as well as the scope of the project and the project plan. The stakeholders (organization) initiating the project should have a good understanding of the project's return on investment (ROI), that is, what is returned at what investment costs. Given this knowledge, a go/no go decision will be made.

## Slide 10: What Does the Development Case Specify?
Artifacts
for the example Core Workflows

## Slide 11: Environment : Focus for Iteration
Prepare the environment:
  process
  guidelines
Development Case
Requirements Attributes Guidelines
Notes: The artifacts listed are from the example Development Case.
Other artifacts may be used as input to these activities.

## Slide 12: Environment: Workflow Detail Diagram
Notes: The circled workflow details and artifacts in the following slides show the focus of effort. They circled items stem from the work (artifacts) specified in the example development case.
Using RUP, locate the Workflow Details and show the artifacts specified in the development case found in the exercise section. Make this module of the course interactive in its use of RUP.

## Slide 13: Requirements : Focus for Iteration
- Define the vision and scope of the system
- Collect functional requirements using storyboarding, brainstorming, etc.
Vision Document
Stakeholder Requests Document
Use Case Specifications
Supplementary Specifications
Requirements Attributes Document
Use Case Model (and Model Survey)
Notes: The stakeholders of the system to be developed (customers, managers, marketing, etc.) work with the System Analysts to define the vision and scope of the project. The driving factor to consider is the user’s needs and expectations. All expressed needs are captured in the Stakeholder Requests document. Some of these will become system requirements. Also considered are constraints on the development project, such as platforms to be supported and external interfaces.
Remind the students that the example Course Registration System is new development which requires several important artifacts.

## Slide 14: Requirements: Workflow Detail Diagram
Notes: Since this is a new system, we will spend time analyzing the problem. We have been given adequate staff, so we can do all the work and don’t have to adjust the scope of the system at this point. Typically new requirements come to light, especially during early iterations. Managing changing requirements in an on-going challenge.
The selected Workflow Details assume that:
1) This is a new system.
2) The work can all be done and there is no redefinition of the Vision
3) New requirements surface during the course of the iteration (Workflow Detail: Manage Changing Requirements).
Using RUP, locate the Workflow Details and show the artifacts specified in the development case found in the exercise section.

## Slide 15: Project Management : Focus for Iteration
- Consider economic factors: costs, resource estimates, revenue projection, etc. - List business risks
- Begin planning at the phase level
Project Plan
Project Schedule
Risk List
Measurement Plan
Business Case Document
Status Assessment
Preliminary Iteration Assessment
Configuration Management Plan
Iteration Plan
Iteration Assessment
Notes: With the input from use-case modeling, it is time to transform the vision into economic terms by considering the project’s investment costs, resource estimates, the development environment needed, the success criteria (i.e., revenue projection and market recognition), and other requirements to initiate the business case. The risk list is updated to include the business risks detected. The project manager builds a phase plan, showing tentative dates for all phases, and the major milestones. The Project Manager begins the software development plan by estimating the development environment needed and the process to be used.
At this stage, the stakeholders of the system to be developed should have a good understanding of the product’s vision and the feasibility of the project. An order of priority among features and use cases is established. The project manager may start planning the project in more detail, basing the project plan on prioritized use cases and associated risk. A tentative set of iterations is defined, with objectives for each.

## Slide 16: Project Management: Workflow Detail Diagram
Notes: We determine the workflow from the fact that this is the first iteration. The Project Manager must also plan for the next iteration. Managing the iteration is an on-going job.
Some of the workflow details for Project Management only occur in the first iteration. They have to do with setting up, or “bootstrapping”, the project.
This activity diagram is a reflection of the dynamic structure of RUP.
Using RUP, locate the Workflow Details and show the artifacts specified in the development case found in the exercise section.

## Slide 17: Evaluating the Inception Iteration
Since this iteration is the only one planned for inception, the Lifecycle Objective Milestone occurs at the end of the iteration
Stakeholders review the artifacts produced and make a “go/no-go” decision
Notes: The stakeholders should have a good understanding of the the project’s return on investment (ROI), that is, what benefit is returned at what investment cost? Given this, they can determine whether to proceed with the project. If they do not feel that enough information is available, or that the collected information is not accurate, they may ask for another iteration before making a decision. This iteration might include prototyping of some high risk area of the project, or doing further market research or competitive assessment, or involving additional users in the process.

## Slide 18: Where Have We Been?
Workflow Details
for the example Core Workflows

## Slide 19: Exercise
Complete Lab Exercises 2 and 3 in the Exercises section of your student manual.

## Slide 20: Case Study: Elaboration Iteration
Project Management
Environment
Business Modeling
Implementation
Test
Analysis & Design
Phases
Process Workflows
Deployment
Configuration & Change Mgmt
Requirements
Elaboration
Inception
Construction
Transition

## Slide 21: Context and Elaboration Iteration Objectives
The Lifecycle Objective milestone was passed and a “go” decision was made
The objectives are to begin to address the architectural risks that have been identified
Most of the effort will be spent in the requirements, analysis & design, and project management workflows
Notes: The majority of Environment activities also take place in Inception and Elaboration. We have omitted a second pass through the Environment workflow for the sake of simplicity.
The goal of this initial iteration is a first cut at the vision and the business case of the project, as well as the scope of the project and the project plan. The stakeholders (organization) initiating the project should have a good understanding of the project's return on investment (ROI), that is, what is returned at what investment costs. Given this knowledge, a go/no- go decision will be made.

## Slide 22: Requirements : Focus for Iteration
- Detail the selected use cases - Begin work on a user-interface prototype - Continue development of the use-case model
Vision Document
Use Case Specifications
Supplementary Specifications
Use Case Model (and Model Survey)
Notes: This is our second pass through this workflow.
A number of use-case specifiers then describe the selected use cases and scenarios in detail. As the model evolves, the system Analyst may restructure the use-case model to improve comprehensibility. The changes to the use-case model and (perhaps) Supplementary Specifications are then reviewed and approved.
The use-case view is revisited again by the architect, taking into consideration new use-case descriptions. The task now is to select what set of use cases and/or scenarios should be analyzed, designed and implemented in the current iteration. The development of these use cases and/or scenarios sets the software architecture. The project manager updates the current iteration plan accordingly. Note that this may include a revision to the risk list if the use-case work done has uncovered new risks or caused a reassessment of priorities.
Using the use cases that have already been fleshed out, a user interface designer starts expanding them into use-case storyboards, and builds a user interface prototype to get feedback from prospective users.
Using RUP, locate the Workflow Details and show the artifacts specified in the development case found in the exercise section.

## Slide 23: Analysis & Design: Focus for Iteration
- Identify classes and organize them into design packages - Define design mechanisms - Consider concurrency and distribution
Software Architecture Document-Use Case, Logical, Process, & Deployment Views
Analysis Model (Logical View)
Design Model (Logical, Component & Process View
Notes: The architect considers the system requirements, the glossary, the use-case view, and the team’s general domain knowledge to sketch an outline of the subsystems, possibly in a layered fashion. The analysis mechanisms are also identified by the architect. The Software Architecture Document is initiated. In parallel with this effort, a team of designers will start finding classes/objects for this iteration’s use cases or scenarios, as well as allocating responsibilities to the identified classes and analysis mechanisms. How the available analysis mechanisms are used by each class is specified. The architect organizes some of the classes into design packages based on the architectural services they provide and relates these packages to the subsystems, repartitioning if necessary.
The architect then derives the design mechanisms needed by the earlier identified analysis mechanisms. These are constrained by the implementation mechanisms available: operating system, middleware, database, etc. These classes are used by designers when describing how the selected use cases or scenarios are realized in terms of collaborating objects in interaction diagrams. This puts requirements on the employed classes and design mechanisms; the interaction diagrams previously created are refined. The designers will merge these requirements into consistent and formal interfaces on their classes. The resulting design artifacts are then reviewed.
Using RUP, locate the Workflow Details and show the artifacts specified in the development case found in the exercise section.

## Slide 24: Evaluating the Elaboration Iteration
Understand the architecture
Realize use cases, based on priority
Design and Implementation models enhanced as necessary
The architect assesses the results of the tests run relative to the evaluation criteria.
The architect and project manager update the risk list.

## Slide 25: Evaluating the Elaboration Iteration (cont.)
The project manager compares the iteration’s actual cost, schedule, and content with the plan, determines if any rework will be done, updates the project plan and upcoming iteration plan as needed.
Design lessons learned from the first cut at the architecture allows refinement of the architectural design in subsequent iterations.
Notes: The stakeholders should have a good understanding of the the project’s return on investment (ROI), that is, what benefit is returned at what investment cost? Given this, they can determine whether to proceed with the project. If they do not feel that enough information is available, or that the collected information is not accurate, they may ask for another iteration before making a decision. This iteration might include prototyping of some high risk area of the project, or doing further market research or competitive assessment, or involving additional users in the process.

## Slide 26: Case Study: Construction Iteration
Project Management
Environment
Business Modeling
Implementation
Test
Analysis & Design
Phases
Process Workflows
Deployment
Configuration & Change Mgmt
Requirements
Elaboration
Inception
Construction
Transition
Notes: The relative amount of work related to the workflows changes between iterations and especially between iterations in different phases.

## Slide 27: Context and Construction Iteration Objectives
It is the middle of the construction phase. Requirements are stable. The architecture is fully implemented. A great deal of functionality has been implemented and integrated
The project is approaching its first “beta” release and the IOC milestone
Most of the effort will be spent in the implementation and test workflows

## Slide 28: Implementation: Focus for Iteration
- Implement new classes - Make approved changes to reused classes - Conduct unit tests
Integration Build Plan
Architectural Prototype - Software Baseline
R 1.0 Software Baseline
Notes: The system integrator determines the order in which subsystems are to be put together to form a working/testable configuration. This depends on the functionality already implemented, and what aspects of the system need to be in place to support the overall integration and test strategy. The results are documented in the Integration Build Plan which defines the frequency of builds and when given “build sets” will be required for ongoing development, integration, and test.
Implementers develop code, in accordance with the project's programming guidelines, to implement the classes in the implementation model. They fix defects and provide any feedback that may lead to design changes based on discoveries made in implementation.
The implementer designs unit tests to address what the unit does (black-box test), and how it does it (white-box test). Under black-box (specification) testing the implementer verifies that the unit, in its various states, performs to its specification, and can correctly handle a range of valid and invalid data. Under white-box (structure), testing the implementer ensures that the design has been correctly implemented and that each decision path can be successfully traversed.
Using RUP, locate the Workflow Details and show the artifacts specified in the development case found in the exercise section.

## Slide 29: Test: Focus for Iteration
- Plan and design system and integration tests for new use cases - Execute the integration and system tests - Perform regression testing on modified classes
Test Plan
Test Procedures
Test Drivers, Stubs, Data & Scripts
Test Evaluation Reports
Notes: The test designer ensures that there will be an adequate number of test cases and procedures to verify testable requirements. The test designer must identify and describe the test cases, and identify and structure the test procedures in the test model. The test designer also reviews the accumulated body of tests from preceding iterations, which could be modified to be re-used in regression testing for the current and future iteration builds.
Integration tests focus on how well, developed components interface and function together. The test designer needs to follow the test plan that describes the overall test strategy, required resources, schedule, and completion and success criteria. The designer identifies the functionality that will be tested together, and the stubs and drivers that will need to be developed to support the integration tests. The implementer develops the stubs and drivers based on the input from the test designer.
Regression testing compares two revisions of the same software and identifies differences as potential defects. It thus assumes that a new software revision should behave like an earlier revision. Regression testing is done after changes are made to the software to ensure that defects have not been introduced as a result of the changes. Regression testing does not introduce new test cases. Its purpose is to verify existing test cases after a software change is made.
Using RUP, locate the Workflow Details and show the artifacts specified in the development case found in the exercise section.

## Slide 30: Evaluating the Construction Iteration
Since there is one more iteration planned for construction, the Initial Operating Capability milestone occurs at the end of the next iteration
Stakeholders review the progress achieved and a decision is made whether the product is ready for release based on
  Number of errors remaining
  Completeness and accuracy of user documentation
Notes: At the end of the construction phase is the third major project milestone (Initial Operational Capability Milestone). At this point, you decide if the software, the sites, and the users are ready to go operational, without exposing the project to high risks. This release is often called a "beta" release.
The evaluation criteria for the construction phase involve the answers to these questions:
  Is this product release stable and mature enough to be deployed in the user community?
  Are all the stakeholders ready for the transition into the user community?
  Are actual resource expenditures versus planned still acceptable?
Transition may have to be postponed by one release if the project fails to reach this milestone.

## Slide 31: Exercise
Complete Lab Exercises 4 and 5 in the Exercises section of your student manual.

## Slide 32: Summary: Iterative Development
Give examples of RUP’s dynamic structure.
How do artifacts develop across the phases and iterations of a lifecycle?
What is the purpose of an iteration plan?
How does the development case guide work with artifacts?